## MOBILE BUGS
Issue | Report | Priority | Status | Comment
Show message on modal that abaddee will review the property when Add property successfullly added | Danish |  | DONE
Message Screen search user change text | Wasiq |  | DONE
Remove Icon red color on search page for favourite property | Wasiq |  | DONE
User info shoud be on property detail page | Wasiq |  | DONE | Need to Ask
Property Detail Images click show on modal or preview | Wasiq |  | DONE
Trusted Agent Pics on Listing | Wasiq |  | DONE
Add Property when select filter close and again open not show value | Wasiq | P6 | DONE
Preview on Map property (Swipe) | Danish | P5 | DONE
Change the Add Property Modal Layout | Danish | P4 | PENDING | Share Design
change marker icon on Map | Wasiq |  | DONE
app Logo icons not reflecting | Wasiq |  | DONE
Message search box not have option to remove previous | Wasiq |  | DONE
Location should be dynamic selected once login | Shariq |  | PENDING | Need to Ask
User profile image not uploading | Shariq |  | PENDING | Need to check image size
Google Login Issue | Wasiq |  | PROGRESS
Restrict Location on Map API | Shariq | P5 | PENDING
Proprty Save not Working | Wasiq |  | DONE
Message Opening on Detail Page | Wasiq | P4 | PENDING
Show Latest Message of A User (Inbox Page) | Wasiq | P4 | DONE | Message
Show Message time as web | Wasiq | P4 | Done
Add Notification count icon on Message | Wasiq | P2 | PENDING
Facebook login (whenever you login with Facebook it creates a new user . so if you logged in with fb and do some work then logged out and when you login in again with the same fb account your work will be lost.)
When we click on All features, it should select all features/facilities
More pictures add option not available
After clicking on submit it should show a message your property is listed and it will listed after aprove by abaadee you will recive a email .
johar app can give the suggestion of gulistan e johar or johar town any area of Pakistan that includes johar
Call button is not working

## UI Bugs
Issue | Report | Priority | Status | Comment

## WEB BUGS
Issue | Report | Priority | Status | Comment

## Android app testing (Engr. Muha
Tester: Engr. Muhammad Hamza Zubair
Abaadee android app testing
Sr. no | Bug Description | Priority | Reported by | Assigned to | Status | Comments (If any)
1 | The first letter of the app name "abaadee" in the app launch icon should be capital i.e "Abaadee" | P3 | Engr. Muhammad Hamza Zubair
2 | There should be space in "Signup" button text on the login page i.e "Sign up" | P3 | Engr. Muhammad Hamza Zubair
3 | There are punctuational and grammatical errors in the terms and conditions agreement on the sign up page. Change the terms and conditions agreement statement to, "I agree to the Terms of Services, Terms of Payment and Privacy Policy | P3 | Engr. Muhammad Hamza Zubair
4 | The text color of all the text box fields should be changed from black to white as black text color is looking dull | P3 | Engr. Muhammad Hamza Zubair
5 | On sign up page if all the fields are not filled, than on clicking on Register button a message is displaying, "You are not agreed with terms & condition" but instead first a message should be displayed, "All fields are mandatory". After filling all the sign up fields and clicking on the register button with out accepting terms and conditions agreement, a message should be displayed, "Please accept terms and conditions agreement" | P3 | Engr. Muhammad Hamza Zubair
6 | The username field should be alphanumeric | P3 | Engr. Muhammad Hamza Zubair
7 | The name field should only accept alphabets and space | P3 | Engr. Muhammad Hamza Zubair
8 | Insert default email format validation and if the enetered email doesn't match with the default format than on clicking on the register button after filling the form, a message should be displayed, "Enter valid email", on the email text box. | P2 | Engr. Muhammad Hamza Zubair
9 | Give an e.g phone number with the phone number field to let the user know that in which format he needs to enter the phone number as there are different formats to enter number. | P2 | Engr. Muhammad Hamza Zubair
10 | Insert phone number format validation as per requirement. Currently there is no validation applied in this field. If the entered phone number doesn't match with the required format than on clicking on the Register button, a message should be displayed, "Invalid number" on the phone number field. | P2 | Engr. Muhammad Hamza Zubair
11 | The phone number field should only accept numbers ( The data type should be Numeric). Currently the data type is VARCHAR i.e allowing the user to enter any type of data. | P2 | Engr. Muhammad Hamza Zubair
12 | Change the sign up message that comes after registration to "Your account has been created successfully. Please check your email". The letter "A" should be in lower case in "Account". Add a full stop after successfully and "P" should be in upper case in "Please" | P3 | Engr. Muhammad Hamza Zubair
13 | On clicking on the Login button without entering Email and Password or by filling just Email or Password a message is displaying, "Some fields are empty". Change this message to "All fields are mandatory" | P3 | Engr. Muhammad Hamza Zubair
14 | The user can login with both email or username so change the name of email text box field to "Email or Username" on Login page | P2 | Engr. Muhammad Hamza Zubair
15 | After logging in, in change password section, on clicking on change password from profile, a message pop up appears. Change the password reset message to, "Password reset code has been sent to your email". "R" and "C" should be in lower case in " Reset Code" and "send" should be changed to "sent". | P3 | Engr. Muhammad Hamza Zubair
16 | After clicking on "OK" on the reset code message pop up, change password screen will be opened. Make the following changes on this screen: a) The "Done" & "Cancel" buttons on this screen should be at the bottom. b)"C" should be in upper case in "Code" text box | P3 | Engr. Muhammad Hamza Zubair
17 | After changing password, a message should be displayed, "Password changed successfully". | P3 | Engr. Muhammad Hamza Zubair
18 | After logging in, if the user uses the back button of the phone to go back, than the sign up message pop up is opening as, "Your account has been created successfully" and the user is logging out. Remove this sign up message pop up + the user is moving to login screen on using the back button of the phone but instead should be moved to the phone's screen by keeping the app in background. (Note: This bug occured multiple times but after that was unable to re-produce it) | P2 | Engr. Muhammad Hamza Zubair
19 | In user's profile, on uploading the image through phone's gallery or camera, most of the images are not uploading due to image size. Increase the image size so that the user could be able to upload image. Currently only some images are uploading which will be irritating for users. | P2 | Engr. Muhammad Hamza Zubair
20 | On uploading the image through gallery or camera, if the image is uploadable (Image size is small), a screen is opening showing the two options 1) Continue button 2) Error text. This screen is useless but instead after uploading the image through gallery or camera, the image should be uploaded directly. | P2 | Engr. Muhammad Hamza Zubair
21 | There is no option available to crop the captured image or image from gallery. After capturing image using camera or selecting image from gallery, the user should be able to crop this image. The image cropping ratio should be 1:1 | P3 | Engr. Muhammad Hamza Zubair
22 | After uploading the image, "Make a choice" dialog box is displaying which opens on selecting the image upload icon in user's profile. This dialog box should not be displayed after uploading the image. | P3 | Engr. Muhammad Hamza Zubair
23 | On searhing any location on the home page, the size of the marker indicating the properties available is very big which is giving a bad look. Reduce the size of this marker. | P3 | Engr. Muhammad Hamza Zubair
24 | Search screen - In filters, in location section, change the "Select City" drop down to search box. It is irritating for users to select city from drop down by searching as compared to search box where user enters the name and a suggestion list opens from which the user just need to select his required option. | P2 | Engr. Muhammad Hamza Zubair
25 | In "Price Range" section inside filters, the unit should be mentioned after price range e.g Price Range (PKR) | P3 | Engr. Muhammad Hamza Zubair
26 | The resolution of the default "Abaadee" image is very low and the color of the image is very dull. Increase the image resolution and change the color code of the default logo image that is displayed when no image is available on the property details page, search screen and on clicking on the available property's marker on the home screen map. | P2 | Engr. Muhammad Hamza Zubair
27 | There is no book marking option on the property details page that comes after selecting any property from the search screen. The bookmark option is just availale on the search screen. | P2 | Engr. Muhammad Hamza Zubair
28 | The bookmarked properties are not displaying in the "Saved" screen available in the bottom navigation bar. Also change "Saved" to "Favourites". After cllicking on the book mark heart option, the heart icon should be filled with red color in order to let the user know that this property has been bookmarked. On again clicking on any bookmarked property, that property should be removed from the "Favourites" section and the heart icon should be unfilled again. | P1 | Engr. Muhammad Hamza Zubair
29 | On searching a property after applying filters, if there is no property available with the required attributes in the filter than after searching no message or screen is opening to let the user know that no property is available with his required attributes. A screen should be opened displaying a message as,("No results found". We can't find any item matching your search) + "Search Again" button. On clicking on this button, the app will take the user to the filters screen. | P2 | Engr. Muhammad Hamza Zubair
30 | On the property details screen, the font size and thickness of the "Call" and "Message" buttons are different. "Message" button font is bold but call button font isn't. Both button font size and style should be similar. | P3 | Engr. Muhammad Hamza Zubair |  | Done
31 | On the property details screen, of each property, our username and profile picture is showing which should not be displayed. The ads are from different stake holders so our profile info shouldn't be displayed on their posts instead the username and the profile picture of the seller should be displayed. | P2 | Engr. Muhammad Hamza Zubair |  | Done
32 | In the property details section, in "Location" segment, unable to navigate the property's location. The user should be able to navigate the location of the property on the map easily. | P2 | Engr. Muhammad Hamza Zubair
33 | The font size of the price of the property should be increased and the color should be be changed from black to orange on the search and property details screen. | P3 | Engr. Muhammad Hamza Zubair
34 | The price format should be changed to the following: e.g "1500000" should be written as "15 lac" (It will be easier for users to see the price in this format) | P3 | Engr. Muhammad Hamza Zubair |  | Not Possible
35 | From the top navigation, go to property listing screen which includes following segments: a) Featured listing b) Pro listing c) Trusted Agents d) Listing The following bugs are there: a) The property price should also be displayed in each segment i.e featured and Pro listing properties. b) The spacing should be same after each segment. Currently the spacing is different after Pro listing and Trusted agents segments. c) The images in the Listing segment are stretched. The image size ratio should be 1:1 | P3 | Engr. Muhammad Hamza Zubair
36 | In filters section, currently the user can select city and location independently i.e can enter any city and a different location of any other city which isn't a location of the entered city but it shouldn't be allowed. Change the location filter in a way that at first the user have to select the the City, after selecting the city, the user will enter the location based on the entered city i.e can only enter the location of that entered city and can't enter any location of a different city. | P2 | Engr. Muhammad Hamza Zubair
37 | The user shouldn't be able to enter any location outside Pakistan. Restrict the location search box only for Pakistan | P2 | Engr. Muhammad Hamza Zubair
38 | The property type should also be displayed on the search screen with in each property description, featured listing, Pro listing and listing sections | P2 | Engr. Muhammad Hamza Zubair
39 | After searching the required property through filters, a list of the searched properties is opened. Go to any other page from bottom navigation bar and than go back to search screen. The search screen will be refreshed and reset but it should not reset and should be continued from the previous stage that the user moved to other screen. | P2 | Engr. Muhammad Hamza Zubair
40 | Add the following options in drawer: a) Home b) New search c) Last search (The previous search should be displayed) d) Favourites e) Contact Us f) About Us | P2 | Engr. Muhammad Hamza Zubair |  | pending | Api issue
41 | In the property details section, the "Message" option to seller should be functional with in app but should not use external messaging services like fb messenger etc. The purpose of messaging is to make the users interact with each other by using the app so it should be with in app. | P2 | Engr. Muhammad Hamza Zubair |  | Done
42 | In filters section, by default the property category i.e "Buy" should be selected from the property category seletion list on the top of the Filter screen because if we aren't selecting the category and doing search by applying other filters than the search is not performing. | P1 | Engr. Muhammad Hamza Zubair |  | Done
43 | The user should also be able to search by applying only a single filter attribute. Currently if I am just selecting property type or Area unit or No of bedroom and doing a search than searh is not performing according to my entered requirements. | P1 | Engr. Muhammad Hamza Zubair |  |  | Api issue
44 | Change "Beds" to "Bedrooms" in filter screen | P3 | Engr. Muhammad Hamza Zubair |  | Done
45 | In filters section, filter by property type, Area Unit, Price range and beds is not working. | P1 | Engr. Muhammad Hamza Zubair |  | Api issue
46 | When internet connection is lost, than on the search screen a "Refresh" button is showing with a text "Not found". It shouldn't be displayed but instead a text should be displayed as "Network Error" as in displaying on"Profile" screen. | P3 | Engr. Muhammad Hamza Zubair
47 | The "Property types" in the filter section and in "Add property" section are different. It should be same in both sections because when a user searches by any particular property type from filters than the searching is performed based on the property type so if the selected property type on the filters screen doesn't match with the property type entered by the seller at the time of adding property than searching will not be performed or the second solution is to add the sub-categories in the property type filter and add all the sub-categories i.e Commercial plot, agricultural land etc in the property type filter so that the searching could also be done according to these sub-categories. | P1 | Engr. Muhammad Hamza Zubair |  | web issue
48 | Sometimes the "Call" and "Message" buttons on the property details page are not working | P1 | Engr. Muhammad Hamza Zubair |  | Some people does not have contact numbers and message is done
49 | On clicking on the markers on the "Home" screen on the locations in which any property is available, the property details window is opening partially but not fully. After selecting any marker, the property window should be opened in full view displaying all of the following property details: a) Title b) Address c) Price d) Property type | P2 | Engr. Muhammad Hamza Zubair |  | Done
50 | In "My Listing" section from drawer, the heading is "Add Listing". Change it to "My Listing" as all the added properties by the user will be displayed here. | P2 | Engr. Muhammad Hamza Zubair |  | Done
51 | In "Add Property" section, on scrolling up the screen the Sale, Rent and Wanted options are moving upward. It should not move on scrolling + the background of this screen should be white. | P3 | Engr. Muhammad Hamza Zubair |  | Done
52 | The name of the "Inbox" section should be changed to "Message" because inbox only contains received messages from other users where as our functionality is different that in this section all the received messages will be displayed + we can also send messages to other users so it is in appropriate to use the word "Inbox" for this section. | P3 | Engr. Muhammad Hamza Zubair |  | DONE
53 | A small red pop up should be displayed on the "Inbox" icon showing the number of un read messages from other users. Once the message is seen than it should be removed but if there are multiple un read messages and the user sees some of them than the no of un read messages should be decreased on pop up. | P2 | Engr. Muhammad Hamza Zubair |  | pending | reason api
54 | In the inbox section, change the drop down to search box. The user should be able to search any user of his choice by entering the username in the search box. The reason to change it to search box is that if the user wants to contact any other particular user than he will have to search the whole drop down list by scrolling down which will be irritating for him. On the other hand by using search box, he can directly type the username in the search box and can send message easily. | P2 | Engr. Muhammad Hamza Zubair |  | Same as web
55 | The messages that we send to others and received messages from other users are displayed below the drop down bar in "Inbox" section. The user's profile image icon size is too big which is giving a bad look, reduce it + reduce the font size of the username that is displayed with it. | P3 | Engr. Muhammad Hamza Zubair |  | pending
56 | The sent messages to other users are taking some time to display the message after sending message to any user in the chat window and all the previous sent messages are refreshed which shouldn't because after sending any message the previous messages vanishes for sometime and are than displayed which doesn't look professional. (Note: The delay shouldn't come in sending message) | P3 | Engr. Muhammad Hamza Zubair |  | Pending | reason api
57 | In "Add property" section, after uploading the property image, the user should also be able to crop that image in a ratio 1:1 + the uploaded picture is showing as horizontally stretched but it should be displayed in 1:1 ratio. | P2 | Engr. Muhammad Hamza Zubair |  | Pending
58 | In "Add property" section, change the name of the field "Beds" to "Bedrooms" | P3 | Engr. Muhammad Hamza Zubair |  | Done
59 | In "Beds" field drop down, the number sequence is out of order + Number "9" is not available. Arrange these numbers in ascending order sequence from (1 - 11). | P2 | Engr. Muhammad Hamza Zubair |  | Same as web
60 | The drop down list numbers are out of order in "Baths" field as well. It should also be arranged in ascending order sequence from ( 1 - 11). | P2 | Engr. Muhammad Hamza Zubair |  | Same as web
61 | After adding property, a pop up message is displaying as, "Property Added successfully". In this messsage, in "Added", letter "A" should be in lower case. | P3 | Engr. Muhammad Hamza Zubair |  | DONE

## Andriod app testing(Taimoor kas
S.NO | BUG DISCRIPTION | PRIORITY | TESTER
1 | No validation of Email is used in the signup process | P2 | Taimoor kashif
2 | NO validation of "Name" is used in the signup process, Only alphabets and space should be entered in the data entery of name | P2 | Taimoor kashif | 16
3 | Same Location is showing on every property detail (current location) except Karachi city | P2 | Taimoor kashif
4 | Map access is not openeing in the details of the property | P3 | Taimoor kashif
5 | The space between the headings and the data is not equal in all the segments i.e Featured listing and trusted agents bith are having diiferent spaces in between heading and text | P3 | Taimoor kashif
6 | Images in the "Listing" category are streched | P3 | Taimoor kashif
7 | Image size present in the ad. of feature listing, pro listing and Listing differ in size | P3 | Taimoor kashif
8 | No logo name in the trusted partner (third logo has no name) | P3 | Taimoor kashif
9 | Call button is not working in some of the ad. | P2 | Taimoor kashif
10 | The added features should be displayed on the screen and a back button should be added to the features adding page | P2 | Taimoor kashif
11 | The added Facilities should be displayed on the screen and a back button should be added to the Facility page | P2 | Taimoor kashif
12 | In the selection of no. of beds ,sequence of numbers is out i.e 1,10,11,2,3….... | P2 | Taimoor kashif
13 | In the selection of no. of Baths, sequence of numbers is out i.e 1,10,2,3….... | P2 | Taimoor kashif
14 | In the selection of no. of Total room, sequence of numbers is out i.e 1,10,11,2,3….... | P2 | Taimoor kashif
15 | Images from gallery are not uploading on to the upload image Option | P2 | Taimoor kashif
16 | A heart Icon to save the property ad. Should be added into the property listing icons sub branches i.e featured listing, prolisting ancd further more | P3 | Taimoor kashif
17 | In search bar when you save any property the heart sign should turn into red filled heart | P3 | Taimoor kashif
18 | The location on search bar should be restricted to Pakistan only | P2 | Taimoor kashif

## Android app testing (Shahzaib I
Bug Report: Abaadee Android Application Tester Name: Shahzaib Idrees
S.No | Bug | Priority | Tester
1 | Same location is showing on every prorperty detail except Karachi (Get current location) | P1 | Shahzaib Idrees
2 | Profile Picture not upload from camera (mentioned the picure size) | P2 | Shahzaib Idrees
3 | Map access is not opening the details of the property | P2 | Shahzaib Idrees
4 | In the selection of number of "Beds" sequence of number is manipulated (i.e 1,10,2,3) | P2 | Shahzaib Idrees
5 | In the selection of number of "Bath" sequence of number is manipulated (i.e 1,10,2,3) | P2 | Shahzaib Idrees
6 | In the selection of number of "Total Room" sequence of number is manipulated (i.e 1,10,2,3) | P2 | Shahzaib Idrees
7 | Property listing icon image are strech | P3 | Shahzaib Idrees
8 | Add Feture are not showing on the display | P2 | Shahzaib Idrees
9 | Add Facilities are not showing on the display | P2 | Shahzaib Idrees
10 | In sign up process "Username" column accept the digits | P1 | Shahzaib Idrees
11 | In sign up process "Phnone number" column accept the alphabets | P1 | Shahzaib Idrees
12 | In sign up process no login from "Facebook" | P1 | Shahzaib Idrees
13 | "Call" and "Message" button are not working in some property | P2 | Shahzaib Idrees
14 | In search bar when you save any property the heart sign should turn into red filled heart | P3 | Shahzaib Idrees
15 | The iamge is doesn't show the Abaadee should contain the logo | P3 | Shahzaib Idrees
16 | In sign up process "Number" column accept the special characters (i.e shahzaib@,#,%,^,&) | P1 | Shahzaib Idrees
17 | In "Phone Number" Column accept above from 11 (i.e 0345-123456789) | P2 | Shahzaib Idrees
18 | App icon "abaadee" in small letter when click abaadee app shows the capital letter "ABAADEE" | P1 | Shahzaib Idrees
19 | In property listing not access the map location direction | P2 | Shahzaib Idrees
20 | In property listing not access to the dial call | P2 | Shahzaib Idrees
21 | In property listing not access to the send message | P2 | Shahzaib Idrees
22 | In sign up process "User Name" accept the special characters (i.e @#$%^&*!) without alphabets and Digits | P1 | Shahzaib Idrees
23 | In sign up process default email validation should be applied (i.e cloud@g"g"mail.com) accept "gg", "gmailmail" | P1 | Shahzaib Idrees
24 | In search bar sometime working or sometime not working | P3 | Shahzaib Idrees
25 | In sign up process "Phone Number" column accept the alphabets and special characters | P1 | Shahzaib Idrees
26 | In sign up process "Username", "Name", "Email", and "Phone Number" column validation should be applied | P1 | Shahzaib Idrees
27 | Add listing property is not showing | P1 | Shahzaib Idrees